## Slide 1: Salesforce/MuleSoft CoE Executive Steering Committee Update
July 20, 2021
PSEG Internal Use Only

## Slide 2: Agenda
Steering Overview
  June → July Outcomes
  Upcoming Decisions
Salesforce CoE Project/Activity Update
  In-Progress
    LI MIMO Phase 1
    NJ CRM Phase 1
    EE/EV
    MWMS
    RCA – LI MIMO Cutover
  Future State
    CRM Phase 2
      NJ
      LI
Additional Topics
  Audit Tracking (SOX) Solution and Budget
MuleSoft CoE Update
Andy to Speak

## Slide 3: Salesforce CoE Project/Activity Update: June/July Outcomes

## Slide 4: June→ July Major Outcomes
LI CRM Phase I RCA
  Findings validated and remediations identified
  High-priority remediations already in work
  Adjusted CoE staffing for DevOps expertise
  Finalizing PSEG formal RCA report in Service Now
Aligned CoE staff to project-specific collaboration
  Joe focused on MWMS with some support for LI Phase 2
  Ken focused on EE/EV with continued support for Enterprise Architecture
  Dustin coordinating business process/requirements across the Salesforce platform
  Umesh coordinating across MuleSoft programs
  Harpal focused on developer experience/DevOps
Established processes for architectural review board (ARB)
  Early iterations of ARB are already underway with inaugural “official” ARB in 2-3 weeks
  Currently finalizing attendees and tailoring process
Ahrey to Speak

## Slide 5: Upcoming Decisions
Before the August Steering Committee, we anticipate the following requests to leadership:
Determine investment to address platform technical debt remediation & Non-Functional Requirements (NFR)
Plan budget & staff to execute RCA recommendations (e.g. DevOps strategy at scale)
Identify Ongoing PSEG COE Resourcing
  Key PSEG Roles
    Platform/Enterprise Architect
    Platform Product Manager
    DevOps and Test Lead
    MuleSoft Resourcing
Umesh to add any Decision Details
Ahrey to Speak

## Slide 6: Salesforce CoE Project/Activity Update: In-Progress Activities by Workstream

## Slide 7: RCA – LI MIMO Cutover
Current Status
  Execute a strategy that aligns LI RCA with platform COE operating model
  Iterate crawl-walk-run execution for all workstreams prioritizing on value, need, and efforts
    Delivered (draft) and operationalizing Developers Guide & Data Migration best practices
    Extend RCA workstreams to LI & NJ platform competencies & practices
    Leveraged tactical issues, e.g., Access Strategy, Audit, to operationalize Architecture Review Board (ARB) cadence across all in-flight projects (CRM NJ Phase 1, LI MIMO Phase 1, MWMS, EE/EV)
    Delivered point of view on DevOps strategy
Plans for Next 2-4 Weeks
  Complete PSEG IT RCA process in Service Now. Done in Parallel with in-progress Action Plan
    Planning for 8/16/21 IT RCA Review. Per request from LOB Teams, will provide Findings and Action Plan update
  Implement environment architecture to facilitate EE/EV ALM
  Implement branching strategy across all in-flight projects
  Deliver end-state findings & recommendations for RCA Items with focus on governance, automation, velocity, agility, & efficiency
  Engage LOB Team members (LI and NJ) for review and input
  Deliver final recommendations on Data Migration best practices and competencies
  Finalize DevOps metrics (and prioritization) & tracking mechanism
Issues/Blockers
  Resource Conflict for PSEG Resources working on this activity and in-flight projects. Managing conflicts for now, but Project Delivery is priority
Management Input Requested
  See slide 5 (Upcoming Decisions)
  PSEG IT Resource – some time spent on non-project activity
Ahrey to Speak

## Slide 8: LI MIMO Phase 1
Current Defect Status- as of Fri, 7/16/21
Plans for Next 2-4 Weeks
  Resolve all remaining High Priority and ‘Must-Do’ Defects to support solution use by LI Team in week of 7/26
  Resolve all remaining defects
Issues/Blockers
  None
Management Input Requested
  Alignment for recommendation to have LI Team use solution prior to all defects being resolved
    Have aligned with LI LOB Team on this recommendation
Andy to Speak

## Slide 9: NJ CRM Phase 1
Current Status
  37 Total Defects
    Open Defects for Data Migration are in-process
      Redeployed resource from LI MIMO Hyper Care to NJ
    Required Audit (SOX) Report is being validated and tested
Plans for Next 2-4 Weeks
  Provide NJ LOB Team Date options for Aug, 2021 Cutover
Issues/Blockers
  Budget for Phase 1
    Sufficient budget through Sept, 2021.
Management Input Requested
  Support for August, 2021 Deployment (exact date tbd)
    Storm Season or High Call Volume
Andy to Speak

## Slide 10: CEF / EE / EV
Current Status
  Provided Project Management application options for the SFDC org
  Drafted an Architecture Review Board Governance document
  Drafted an Architecture Review Board Process Flow
  Developing an environment management and branching strategy to support application lifecycle management milestones, in concert with platform best practices
Plans for Next 2-4 Weeks
  Complete, obtain approval, and publish the Architecture Review Board Governance document and Architecture Review Board Process Flow
  Kickoff the Architecture Review Board meetings and regular cadence
  Complete the documentation of the Salesforce Knowledge Articles process flow and sharing configurations, esp. as required for CEF EE EV. (PSEG must perform the configurations in the PSEG production system(s))
Issues/Blockers
  None
Management Input Requested
  None
Ahrey to Speak

## Slide 11: MWMS
Current Status
  Review performance test results & provide insights to areas of improvement & standardization
  Crosswalk LI RCA lessons learned and implementation with MWMS
  Progressing with mapping of fields to match fields in AWS Glue (~30 reports mapped)
  Work on SOQL queries is moving along – first 5 reports have prototypes for the business to review
    Got team unstuck after returning from vacation
    Developed queries to kickstart progress
Plans for Next 2-4 Weeks
  Deliver additional field mapping sessions for next batch of reports
  Implement SOQL queries for the next batch of reports (6 onward)
Issues/Blockers
  None
Management Input Requested
  None
Ahrey to Speak

## Slide 12: Salesforce CoE Project/Activity Update: Future State Activities

## Slide 13: CRM Phase 2 - NJ
Current Status
  CRM Phase 2 Roadmap Option has been defined based on latest SLT feedback (mid-July)
    Includes Timeline & Release, Spend Plan and Business Value/KPI Analysis
Plans for Next 2-4 Weeks
  Present updated CRM Phase 2 Roadmap recommendation to PSEG LOB and IT SLT
  Based on guidance/decision provided, take appropriate next steps for project preparation
Issues/Blockers
  None
Management Input Requested
  Post SLT Approval will need guidance on project preparation and transition into Energy Cloud Program
Andy to Speak

## Slide 14: CRM Phase 2 - LI
Current Status
  Story sizing is almost complete with the business
    Reviewing last batch of stories with the business
  Stories are ~90% properly sized and ready for LOB/Tech review & estimate
    Worked on sizing stories while team was working on high priority deployment related work
Plans for Next 2-4 Weeks
  Sessions with technical team to review scope and give SWAGs for stories
  Resume cadence of meetings interrupted by high priority work from deployment
  Continue NJ and LI CRM Phase 2 Requirements Reusability Analysis
  Complete Cost and Timeline estimates by end Aug, 2021
Issues/Blockers
  None
Management Input Requested
  Budget required to deliver Phase 2 will require URB to support additional funding
Andy to Speak

## Slide 15: Additional Topics

## Slide 16: Audit Tracking (SOX) Solution
Current Status
  Salesforce Audit Tracking POC Solution was presented to all Stakeholder Teams and Approved
    Budget Estimate for this activity is
      Project Costs: $200K (1x Capital Implementation Costs)
      Run Costs: $25K (AWS Service and Internal IT Support)
  SAP SSO Solution Option was also estimated
    Project Costs
      $700K in SSO Licenses for Enterprise
      $200K for Implementation/Integration
    Run Costs
      $140K (SAP License Maintenance Cost)
  Recommendation is POC Solution
Plans for Next 2-4 Weeks
  Confirm Funding Timeline with plan to deploy by end 2021
Issues/Blockers
  Funding for this project. Needed prior to CRM Phase 2, but CRM Phase 1 does not have sufficient budget
Management Input Requested
  Approval to proceed with POC Solution
  Have approval from EE/EV Project to pay for the 1x Implementation Costs
    Run Costs would be Fair Share allocation across 3 LOBs utilizing Salesforce platform
Andy to Speak

## Slide 17: MuleSoft CoE Project/Activity Update

## Slide 18: Status
CoE Operating Model
  Vision
  Roles & Responsibilities
Project Execution Process
  Integration deliverables at each stage
  Task definition by role by stage
  Estimator tool
Interview Process
Bi-weekly Developer Forum
EE/EV Developer Onboarding
Confluence Organization
Hiring API Architect, Platform Owner
Project Oversight
  EE/EV CoE Pilot
  OMS, GIS
  CRM Phase 1
Define Technical Assets
  Templates
  Standards
  Guidelines
Synergy
  GPM
  NJ – LI alignment
Platform Readiness for Storm (DR, Availability, Bandwidth)
CoE Staffing
  Build common technical assets
  Project oversight
Operating Model Transition
Early engagement of CoE for Scope & User Stories Definition
Budget for Platform Readiness for Storm
Dedicated Testing Teams
Expedited Security Approvals
Accomplishments
Current Priorities
Critical Success Factors
Notes: CoE Staffing:
  Resource hiring is slow so Umesh is pulled in to project instead of building foundational items( standards & guidelines)
  We may have to leverage MuleSoft in the interim; also looking at other vendors like cognizant
  Charge back : Need for core cost allocation for CoE
Operating Modeling Transition :
  3 months back we planned for centralized but all the new initiatives are project based. We need more architects to support project with integration governance
  Need one more architect
  Evangelization(Think of CoE first) – meeting with GPM and email communication
User Stories: They are not complete; hiring a development team before completing user stories are not prudent. We observed this in EE/EV, we are going to talk to Venky to address this
Testing practice / CoE : Managing environments, data quality & testing should be centralized
Budget for platform readiness: Direct connect

## Slide 19: Critical Success Factors
 | Issues | Resolution
CoE Staffing | Lack of qualified resources to build PoCs & foundational technical assets (e.g. standards, guidelines, etc.) | Hiring for 1 Architect, 1 Platform Owner underway Need to hire 1 more Architect - Gap Use project resources to build PoCs until CoE is staffed
Transition from Project Based Model to Centralized Operating Model | PSEG team is used to working in a project based model which is silo-ed and lacks standard governance Projects have not budgeted for CoE resources CoE pulled in at the last minute | Current and future RFP projects must allocate budget for CoE resources Projects must engage CoE at the beginning before defining RFP
User Stories | User stories for projects are not detailed & lacks clear acceptance criteria Hiring a development team before detailed user story is not efficient way to utilize budget | Leverage Business Analyst & utilize CoE team to write detailed requirements Onboard development teams complete user story review
Testing | PSEG lacks a centralized testing team. Integration developers are expected to participate full time in end 2 end testing. Data quality & environment mapping for testing is not properly managed. | Unit testing will be performed by developers. All other testing to be driven by centralized testing team. Defects to be addressed by Integration developers
Security Approvals | In some cases, Security approvals have taken a long time. Lack of Cloud resources are adding more delays | Help project teams assess and plan ahead any security approvals needed Engage security architect to review all
Notes: E2E Testing : This is not an efficient use of integration resources. Testing team should own data quality of testing environments

## Slide 20: EE / EV
Integration Status as of 07/09/2021 Cognizant team is onboarded and MuleSoft CoE architect is identified. Detailed MuleSoft onboarding of new team was conducted to help accelerate their design & development phase. Team is reviewing the user stories and defining detailed requirements. |  | GPM / Project Stakeholders | Venky Bogam– Group Product Manager Naresh Motiani – Architect |  | Scope | Schedule | Outcome
 |  |  |  |  | Y | G | G
 |  | PSEG CoE Resources | (Architect developers) Umesh Ranganathan |  |  |  | 
 |  | Milestone | Release 1 integration scope & detailed user stories |  |  |  | 
Completed API and integration activities | Active API and integration activities |  |  | Upcoming API and integration activities |  |  | 
Developer onboarding Process walk through Architecture session Standards overview Shared lessons learnt from other projects & identified key action items & risks Firewall requests Security review for external access | Developed use cases to help developers to understand PSEG architecture & standards User stories review ; enhance user stories with detailed requirements Help define non functional requirements for various use cases Identified a full time MuleSoft Architect to help with governance & technical oversight |  |  | Finalized integration scope for Release 1 Fully defined user stories Project plan with detailed task & milestone |  |  | 
API and integration Risk & Challenge | API and integration Action | API and integration Comments
Project is in stage 5, we don’t have all the required deliverables from pervious stages e.g. integration roadmap | Umesh to perform a gap analysis and complete any missing document | Working with the team to come up with integration roadmap and phased integration architecture
The scope of integrations are dependent on few key open decisions | Project team is aware of these decision points and working to resolve them | Open decision: Will Independent Contractors(IC) work in their CRM or leverage PSEG CRM? Impact to Intg. scope
User stories don’t have detailed information to be able to start the design | Working with the team to understand scope, define detailed functional & non functional requirements | 
Stage: Design(stage 5)
DRAFT

## Slide 21: Appendix

## Slide 22
Experimentation
RCA Execution Plan
All Work Streams are On Track
Aligned to Priorities
Iterate to the Optimum Solution
Incremental Outcomes
  LI MIMO - Root Cause Analysis (RCA)

## Slide 23: Key Insights Summary – Initial SFDC CoE POV (March, 2021)
KEY ISSUES/FINDINGS
Governance & Alignment
experience, vision, and priorities require identifying owners for transformation with data councils, steering committees, review boards and IT engagement.
Lack Measurable Outcomes
There are no/limited guidelines for establishing, tracking, and measuring ROI on technology investments.
Disparate Systems
siloed systems cause excessive swivel chair, data quality issues, inefficiencies, inconsistencies and more integration.
Data Access
hinders ability to manage unified customer 360 and front to back office consistency.
Reliance on Manual Processes
impacts customer experience, employee productivity & causes revenue leakage.
Ineffective Integration
integrations are P2P rather than decoupled, reusable & composable building blocks.
EARLY PHASE FOCUS
Define & Refine
CoE initiative to drive strategic business and technology programs to tightly align business and IT functions under CoE Authority
Simplify
merge siloed, disparate, redundant systems and manual processes into a unified platform to manage customers and partners across programs.
Enable & Engage
Align on PSEG principles that establish and drive ROI, which can be owned by the CoE, not by individual business areas.
Aggregate
source systems through single lens to enable holistic customer view & eliminate data/operational redundancies.
Create
center of excellence program to drive strategic technology initiatives to tightly align business and IT functions.
BUSINESS DRIVERS
Increase
Visibility and ability to measure ROI on technology investments
Improve
Budget Allocation, Systems Development and Pace of Innovation with effective Factory Operations
Maximize
Adoption of new offerings (e.g., CEF) through vastly improved focus on the customer (Customer 360)
Facilitate
Collaboration across all PSEG operating units to deliver consistent, targeted, personalized services to PSEG customers
Prioritize
Customer Centricity, Delivery Consistencies, and Process Efficiencies
Optimize
Allocation of Human Capital by leveraging technology best practices and North Star artifacts
STRATEGIC OBJECTIVES
Growth
Cross-sell - upsell as the preferred Electric and Gas provider; to service those segments and grow Electric Vehicle (EV) and Energy Efficiency (EE) programs.
Customer & Agent Engagement
best-in class Customer Service experience coupled with power to engage and drive PSEG loyalty and relationships.
Innovation
Drive operational excellence & thought leadership in the development and delivery of a comprehensive Clean Energy Future program to meet the needs of a diverse customer base.
Digital Operating Model
agile, composable, foundation for execution based infrastructure to maximize investments in SF and drive IT and Business alignment.

## Slide 24
Business Process
BRS
Collection
Case Management
TBD
Appliance Service Business
Channel Management
Marketing Cloud
Analytics
Sales Cloud
Requirements
Design & Development
Test
Implementation
> 60%
40% - 60%
20% - 40%
< 20%
Reuse Factor
Reusable Components
TBD
* Preliminary assessment, LI user story grooming in progress
LI & NJ CRM Reusability Analysis*
Data Migration
Integration
Notes: Business process similar payment plan, consumption history, billing history, case types
Collection LI uses Conga, similar DPA process
Business Renovation Services not in NJ
Channel Mgmt in LI focuses on external KM and Chatbot to manage cases/LCS
Sales Cloud focuses on LCS and account hierarchy, shares common integration with Outlook / LCS