## Slide 1: EPMO Stage Gate Process Framework
November 2020

## Slide 2: Stage Gate Process Framework: Review, Refine & Finalize
Feedback COB
Mon 11/23
Stage Gate Process Materials Sent Wed 11/18
Refine w/ Feedback Wed 11/25
Distribute Final
Fri 11/27
Review Meeting
Thurs 11/19
Timeline
Agenda for Review Meeting on Thurs 11/19:
40 Min Overview of Materials
  Project Categorization
  IT Stage Gate Process Framework
  SDLC Categories & Attributes
  SGP Tailoring for SDLC
  SGP Tailoring for Categories
  SGP Scorecards
  Status Reporting Process – to be sent separately
20 Min Q&A

## Slide 3: Project Categorization Matrix
Complexity Attributes | Formal Gated ( >$500k ) | Informal Gated (Greater than $250k - $500k) | Informal Gated (Less than $250k) | Miscellaneous Effort | Annual/Routine Effort
Staffing Profile | PM & Scheduler & Controller | PM & Scheduler & Controller | PM & Scheduler & Controller | PM (Optional: Scheduler & Controller) | PM (Optional: Scheduler & Controller)
Description | Very large projects that may be high Financial and involve a large team and impact the entire enterprise or many organization. Highly visible and high in financial risk. | This category includes more typical projects that are medium risk in terms of technology and the business with higher chance of success. | This category includes more typical projects that are low medium risk in terms of technology and the business with higher chance of success. | Very low risk or very small, short duration projects. These are repeatable projects, typically familiar, off the shelf technology. Many projects are done during a typical year and they do not have any major constraints. | Projects that are held every year routinely such as, Server Refresh and some Telecom Projects.
Size |  |  |  |  | 
Financial (incl. required labor) | >$500k * | $251k - $500k | $100k-$250k | <$100k | Varies by Project
Labor Hours | >5,000 hours | >2,000 hours | >1,000 hours | <1,000 hours | Varies by Project
# BU's impacted | 1 or more | 1-4 | 1-4 | 1 | > 1
Estimated number of tasks | >500 | >100 | >100 | <100 | Varies by Project
# of Vendors Involved | 1 or more | Up to 5 | Up to 5 | 1 or less | 1
System Integration | High | Medium | Low | Some | Some
Risk |  |  |  |  | 
Business Case Risk Class | High Risk/Medium Risk | Medium risk | Low Risk | Low risk | Low risk
Duration | Can be a single or a multiyear | <1 year | <1 year | <6 mos | 1 year
Dependencies on Other Project/Initiatives | High/Medium | High | Medium | None | None
Technical | High Risk/Medium Risk | Medium risk | Low Risk | Low risk | Low risk
Enhancement to Existing System | Yes/No | Yes/No | Yes/No | Yes | Yes
New System: |  |  |  |  | 
Unproven Tech | Yes/Maybe | Maybe | Maybe | Seldom | None
COTS-Customization Level | High/Medium | Medium | Low | None | None
Solution Complexity | High/Medium | Medium | Medium | Low | Low
Business (Regulatory/ Compliance) | High | Medium | Low | Low | Varies by Project
Customer Constraints (Availability, Business Deadlines, Commitment) | High | Medium | Medium | Low | Low
Visibility |  |  |  |  | 
Urgency | Critical/Necessary | When possible | When possible | When possible during budgeted year | High/Medium
Priority | High/Medium | Medium | Medium | Low | Medium
Constraint (Financial/Schedule - storms, Outages) | Some | Some | Some | Few, possible schedule | Very Few
Financial Management |  |  |  |  | 
Financial Reporting | Very Comprehensive | Somewhat Comprehensive | Somewhat Comprehensive | Regular | Intermittent
Financial Management | Intense | Somewhat Intense | Some | Adequate | Minimal
Guidance for Business Driven projects: These are projects that are not entirely led by IT and funding case/approval is driven by another business function. However, IT has a sub-project(s) under the overall funding which has its own project code(s). The categorization below should be followed with identified SGP modifications which can be found with green stars.
* The budget threshold for SGP categories may vary by tower. e.g. Towers may supply justifications for $5M and up to be formal gated with below that to be informal gated.

## Slide 4: IT Stage Gate Process Framework: Waterfall
Create
Concept
Develop Press Release
Project
Initiation
Develop Initial Design
Design
Direct &
Manage
Post Deployment
Review Concept
GATE
Press Release Challenge
GATE
Initial Readiness
GATE
Initial Design
GATE
Definitive Estimate GATE
Production Readiness GATE
Project Closeout
GATE
 | Create Concept | Develop Press Release | Project Initiation | Develop Initial Design | Design | Direct & Manage | Post Deployment
Stage Objective | Establish a business opportunity or need Gain approval for further investment in the Press Release (business justification) | Develop the full Press Release for funding approval Determine feasibility of each alternative solution | Define scope and high level plan Onboard the PM and develop a Project Management Plan Kickoff the project | Complete detailed analysis and refine plan based on approved requirements Begin vendor selection process based on refined scope and requirements | Complete detailed design on chosen solution with involvement of selected vendor Use detailed design to refine plan and estimate | Execute the detailed plan and deliver the Press Release product scope | Finalize project management deliverables, transition to Operations Support team and closeout the project Actualize the business objectives and value from the Press Release Put the asset in service
Checklist | Begin Press Release: Executive Summary Scope and Boundaries Strategic Initiative Alignment Identify Business Sponsor Identify Project Sponsor Identify SMEs Identify and Involve Project Manager (Optional) Identify Technical Lead/Analyst (Optional) Estimate of Capital Investment Estimate of O&M Investment Proposed Project Request (PPR) / Expected Benefits Action Plan BU Driven Only: Skip stage/gate | Identify Primary Products or Deliverables Define High Level Milestones Plan Finalized Press Release (Service Now): Refined Implementation Cost (Capital and O&M) Ongoing Annual O&M Cost Reduced Cost Benefits Avoided Cost Benefits Qualitative Risk Assessment Identify and Involve Project Manager (Optional) Identify Technical Lead/Analyst (Optional) BU Driven Only: Complete all except: Costs & Benefits Skip gate URB approved PEEM Phase 0 process | Complete IT Project Categorization Assignment of PM, if not Identify Technical Lead/Analyst Identify owner for change plan Complete Project Charter (template) and Approval Document GOES Model (template) Identify Impacted Business Processes Identify needed RFIs or RFPs Develop Initial Schedule (template) Ensure Project Codes Ready for Use Complete Qualitative Risk Assessment Complete Project Management Plan (template) – Combining with Project Charter Hold Project Kickoff Schedule Initial Steering Committee Meeting | Delivery of RFI or RFP Baseline Schedule and Financials Complete Quantitative Risks Assessment Revise budgetary estimates Complete high level design (template) Obtain Detailed Requirements Approval (template) Create Test Management Plan Complete Change Mgmt. Needs Assessment Create Change Mgmt. Plan (template) Create Requirements Traceability Matrix | Complete System Design Specs (template) Revise Estimate/Submit Def. Est. / Project CR for approval Re-baseline Schedule and Financials Update Risks and Issues Updated Risk Contingency Estimates Updated Requirements Traceability Matrix Define Test Cases Execute Communication Plan | Update Project Risks/ Issues Document Lessons Learned Obtain IT Change Control Board Approval for Implementation Produce Test Case Results and Test Results Artifacts Document Deployment Mgmt. Plan Document Runbook Conduct Operational Readiness Review, obtain Acceptance from Operations, and Production Acceptance approval | Complete Post Deployment Support (Hypercare) Close Project Risks and Issues Update Lessons Learned Put Work Order(s) In-Service Finalize Schedule Finalize Financials Finalize Project Artifact Archival Closeout project
 | Estimate Maturity: -50%/+100% | Estimate Maturity: -50%/+50% | Estimate Maturity: -50%/+50% | Estimate Maturity: -20%/+30% | Estimate Maturity: -10%/+15% | Estimate Maturity: -10%/+10% | Estimate Maturity: Actualized

## Slide 5: IT Stage Gate Process Framework: Waterfall
Create
Concept
Develop Press Release
Project
Initiation
Develop Initial Design
Design
Direct &
Manage
Post Deployment
Review Concept
GATE
Press Release Challenge
GATE
Initial Readiness
GATE
Initial Design
GATE
Definitive Estimate GATE
Production Readiness GATE
Project Closeout
GATE
 | Create Concept | Develop Press Release | Project Initiation | Develop Initial Design | Design | Direct & Manage | Post Deployment
Stage Objective | Establish a business opportunity or need Gain approval for further investment in the Press Release (business justification) | Develop the full Press Release for funding approval Determine feasibility of each alternative solution | Define scope and high-level plan Onboard the PM and develop a Project Management Plan Kickoff the project | Complete detailed analysis and refine plan based on approved requirements Begin vendor selection process based on refined scope and requirements | Complete detailed design on chosen solution with involvement of selected vendor Use detailed design to refine plan and estimate | Execute the detailed plan and deliver the Press Release product scope | Finalize project management deliverables, transition to Operations Support team and closeout the project Actualize the business objectives and value from the Press Release Put the asset in service
Checklist | Begin Press Release: Executive Summary Scope and Boundaries Strategic Initiative Alignment Identify Business Sponsor Identify Project Sponsor Identify SMEs Identify and Involve Project Manager (Optional) Identify Technical Lead/Analyst (Optional) Estimate of Capital Investment Estimate of O&M Investment Proposed Project Request (PPR) / Expected Benefits Action Plan BU Driven Only: Skip stage/gate | Identify Primary Products or Deliverables Define High Level Milestones Plan Finalized Press Release (Service Now): Refined Implementation Cost (Capital and O&M) Ongoing Annual O&M Cost Reduced Cost Benefits Avoided Cost Benefits Qualitative Risk Assessment Identify and Involve Project Manager (Optional) Identify Technical Lead/Analyst (Optional) BU Driven Only: Complete all except: Costs & Benefits Skip gate URB approved PEEM Phase 0 process | Complete IT Project Categorization Assignment of PM, if not Identify Technical Lead/Analyst Identify owner for change plan Complete Project Charter (template) and Approval Document GOES Model (template) Identify Impacted Business Processes Identify needed RFIs or RFPs Develop Initial Schedule (template) Ensure Project Codes Ready for Use Complete Qualitative Risk Assessment Complete Project Management Plan (template) – Combining with Project Charter Hold Project Kickoff Schedule Initial Steering Committee Meeting | Delivery of RFI or RFP Baseline Schedule and Financials Complete Quantitative Risks Assessment Revise budgetary estimates Complete high-level design (template) Obtain Detailed Requirements Approval (template) Create Test Management Plan Complete Change Mgmt. Needs Assessment Create Change Mgmt. Plan (template) Create Requirements Traceability Matrix | Complete System Design Specs (template) Revise Estimate/Submit Def. Est. / Project CR for approval Re-baseline Schedule and Financials Update Risks and Issues Updated Risk Contingency Estimates Updated Requirements Traceability Matrix Define Test Cases Execute Communication Plan | Update Project Risks/ Issues Document Lessons Learned Obtain IT Change Control Board Approval for Implementation Produce Test Case Results and Test Results Artifacts Document Deployment Mgmt. Plan Document Runbook Conduct Operational Readiness Review, obtain Acceptance from Operations, and Production Acceptance approval | Complete Post Deployment Support (Hypercare) Close Project Risks and Issues Update Lessons Learned Put Work Order(s) In-Service Finalize Schedule Finalize Financials Finalize Project Artifact Archival Closeout project
 | Estimate Maturity: -50%/+100% | Estimate Maturity: -50%/+50% | Estimate Maturity: -50%/+50% | Estimate Maturity: -20%/+30% | Estimate Maturity: -10%/+15% | Estimate Maturity: -10%/+10% | Estimate Maturity: Actualized
CoE | Identify data flow in business process Identify platforms / applications impacted | Identify data entities for integration Estimate integration & data migration Support scoping & budgeting | Define Integration Roadmap Define Integration Architecture Review standards & define non- functional requirements Architecture Review Board review | Reuse analysis Define Acceptance criteria Identify system of record Identify frequency/ batch | Design review Finalize Deployment architecture vCore analysis | Code review Go-live checklist review Operation plan review Technical Debt review | Update exchange Update platform KPIs Review performance actual vs planned

## Slide 6: IT Stage Gate Process Framework: Waterfall
Create
Concept
Develop Press Release
Project
Initiation
Develop Initial Design
Design
Direct &
Manage
Post Deployment
Review Concept
GATE
Press Release Challenge
GATE
Initial Readiness
GATE
Initial Design
GATE
Definitive Estimate GATE
Production Readiness GATE
Project Closeout
GATE
 | Create Concept | Develop Press Release | Project Initiation | Develop Initial Design | Design | Direct & Manage | Post Deployment
Stage Objective | Establish a business opportunity or need Gain approval for further investment in the Press Release (business justification) | Develop the full Press Release for funding approval Determine feasibility of each alternative solution | Define scope and high-level plan Onboard the PM and develop a Project Management Plan Kickoff the project | Complete detailed analysis and refine plan based on approved requirements Begin vendor selection process based on refined scope and requirements | Complete detailed design on chosen solution with involvement of selected vendor Use detailed design to refine plan and estimate | Execute the detailed plan and deliver the Press Release product scope | Finalize project management deliverables, transition to Operations Support team and closeout the project Actualize the business objectives and value from the Press Release Put the asset in service
Checklist | Begin Press Release: Executive Summary Scope and Boundaries Strategic Initiative Alignment Identify Business Sponsor Identify Project Sponsor Identify SMEs Identify and Involve Project Manager (Optional) Identify Technical Lead/Analyst (Optional) Estimate of Capital Investment Estimate of O&M Investment Proposed Project Request (PPR) / Expected Benefits Action Plan BU Driven Only: Skip stage/gate | Identify Primary Products or Deliverables Define High Level Milestones Plan Finalized Press Release (Service Now): Refined Implementation Cost (Capital and O&M) Ongoing Annual O&M Cost Reduced Cost Benefits Avoided Cost Benefits Qualitative Risk Assessment Identify and Involve Project Manager (Optional) Identify Technical Lead/Analyst (Optional) BU Driven Only: Complete all except: Costs & Benefits Skip gate URB approved PEEM Phase 0 process | Complete IT Project Categorization Assignment of PM, if not Identify Technical Lead/Analyst Identify owner for change plan Complete Project Charter (template) and Approval Document GOES Model (template) Identify Impacted Business Processes Identify needed RFIs or RFPs Develop Initial Schedule (template) Ensure Project Codes Ready for Use Complete Qualitative Risk Assessment Complete Project Management Plan (template) – Combining with Project Charter Hold Project Kickoff Schedule Initial Steering Committee Meeting | Delivery of RFI or RFP Baseline Schedule and Financials Complete Quantitative Risks Assessment Revise budgetary estimates Complete high-level design (template) Obtain Detailed Requirements Approval (template) Create Test Management Plan Complete Change Mgmt. Needs Assessment Create Change Mgmt. Plan (template) Create Requirements Traceability Matrix | Complete System Design Specs (template) Revise Estimate/Submit Def. Est. / Project CR for approval Re-baseline Schedule and Financials Update Risks and Issues Updated Risk Contingency Estimates Updated Requirements Traceability Matrix Define Test Cases Execute Communication Plan | Update Project Risks/ Issues Document Lessons Learned Obtain IT Change Control Board Approval for Implementation Produce Test Case Results and Test Results Artifacts Document Deployment Mgmt. Plan Document Runbook Conduct Operational Readiness Review, obtain Acceptance from Operations, and Production Acceptance approval | Complete Post Deployment Support (Hypercare) Close Project Risks and Issues Update Lessons Learned Put Work Order(s) In-Service Finalize Schedule Finalize Financials Finalize Project Artifact Archival Closeout project
 | Estimate Maturity: -50%/+100% | Estimate Maturity: -50%/+50% | Estimate Maturity: -50%/+50% | Estimate Maturity: -20%/+30% | Estimate Maturity: -10%/+15% | Estimate Maturity: -10%/+10% | Estimate Maturity: Actualized
CoE | Identify data flow in business process Identify platforms / applications impacted | Identify data entities for integration Estimate integration & data migration Support scoping & budgeting | Define Integration Roadmap Define Integration Architecture Review standards & define non- functional requirements Architecture Review Board review | Reuse analysis Define Acceptance criteria Identify system of record Identify frequency/ batch | Design review Finalize Deployment architecture vCore analysis | Code review Go-live checklist review Operation plan review Technical Debt review | Update exchange Update platform KPIs Review performance actual vs planned

## Slide 7: IT Stage Gate Process Framework: Agile SDLC
Create
Concept
Develop Press Release
Project
Initiation
Sprint/Release
Post
Deployment
Review Concept
GATE
Press Release Challenge
GATE
Initial Readiness
GATE
Initial Design
GATE
Definitive Estimate GATE
Production Readiness GATE
Project Closeout
GATE
 | Create Concept | Develop Press Release | Project Initiation | Plan | Sprint/Release | Refine | Post Deployment
Stage Objective | Establish a business opportunity or need Gain approval for further investment in the Press Release (business justification) | Develop the full Press Release for funding approval Determine feasibility of each alternative solution | Finalize Product Roadmap and Release Planning Initiate Product Backlog Onboard the PM/Scrum Master and develop a Project Management Approach Kickoff the project | Define the details of the features and/or solution supporting achievement of the MVP Size stories in prioritized backlog (e.g. t-shirt sizes) and conduct sprint planning Establish acceptance criteria to support ‘done’ state from end user perspective | Execute work approved for sprint Conduct demonstration of completed features with product owner against acceptance criteria Agree on features to be release and quality assurance procedures | Conduct sprint retrospective for continuous improvement of team performance and execution Refine backlog and reprioritize based on Product Owner input/feedback | Finalize project management deliverables, transition to Operations Support team and closeout the project Actualize the business objectives and value from the Press Release Put the asset in service
Checklist | Begin Press Release: Executive Summary Scope and Boundaries Strategic Initiative Alignment Identify Business Sponsor Identify Product Owner Identify SMEs Identify and Involve Project Manager (Optional) Identify Technical Lead/Analyst (Optional) Estimate of Capital Investment Estimate of O&M Investment Proposed Project Request (PPR) / Expected Benefits Action Plan BU Driven Only: Skip stage/gate | Identify Primary Products or Deliverables Define High Level Milestones Plan Finalized Press Release (Service Now): Implementation Cost (Capital and O&M) Ongoing Annual O&M Cost Reduced Cost Benefits Avoided Cost Benefits Qualitative Risk Assessment Identify and Involve Project Manager (Optional) Identify Technical Lead/Analyst (Optional) BU Driven Only: Complete all except: Costs & Benefits Skip gate URB approved PEEM Phase 0 process | Complete IT Project Categorization Assign PM / Scrum master Identify Technical Lead/Analyst Identify owner for change plan Document GOES Model (template) Identify Impacted Business Processes Develop Initial Schedule (template) Ensure Project Codes Ready Complete QRA Complete Project Management Plan Approach Hold Project Kickoff Schedule Initial Steering Committee Meeting Define Minimum Viable Product Create and Obtain Approval of Product Roadmap Buildout Backlog of Epics Create Test Management Approach/Acceptance Criteria Identify needed RFIs or RFPs | Complete/Revise Quantitative Risks Assessment Complete/Revise Change Mgmt. Needs Assessment Create/Revise Change Mgmt. Plan (template) Establish/Revise User Stories Groom Backlog Agree on Sprint Scope Share Upcoming Release Features Revise Schedule and Financials | Validation of Acceptance Criteria Update Risks and Issues Define Test Cases Product feature demonstration Burndown and Velocity Metrics Monitor Story Point Debt Definitive Estimate gate is required after 20% of Sprints are completed | Update Project Risks/ Issues Document Lessons Learned Obtain IT Change Control Board Approval for Release Produce Test Case Results and Test Results Artifacts Document Release Deployment Plan Obtain Product Owner Acceptance of User Stories Conduct Release Readiness Review, obtain Acceptance from Operations and obtain Production Acceptance approval Distribute Release Notes, including UI and Feature – Function Descriptions | Complete Post Deployment Support (Hypercare) Close Project Risks and Issues Update Lessons Learned Put Work Order(s) In-Service Finalize Schedule Finalize Financials Finalize Project Artifact Archival Closeout project
 | Estimate Maturity: -50%/+100% | Estimate Maturity: -50%/+50% | Estimate Maturity: -50%/+50% | Estimate Maturity: -20%/+30% | Estimate Maturity: -10%/+15% | Estimate Maturity: -10%/+10% | Estimate Maturity: Actualized
Plan
Refine
CoE
CoE | Identify data flow in business process Identify platforms / applications impacted | Identify data entities for integration Estimate integration & data migration Support scoping & budgeting | Define Integration Roadmap Define Integration Architecture Review standards & define non- functional requirements Architecture Review Board review | Reuse analysis Define Acceptance criteria Design review | Finalize Deployment architecture vCore analysis Code review | Go-live checklist review Operation plan review Technical Debt review | Update exchange Update platform KPIs Review performance actual vs planned

## Slide 8: IT Stage Gate Process Framework: Agile SDLC
Create
Concept
Develop Press Release
Project
Initiation
Sprint/Release
Post
Deployment
Review Concept
GATE
Press Release Challenge
GATE
Initial Readiness
GATE
Initial Design
GATE
Definitive Estimate GATE
Production Readiness GATE
Project Closeout
GATE
 | Create Concept | Develop Press Release | Project Initiation | Plan | Sprint/Release | Refine | Post Deployment
Stage Objective | Establish a business opportunity or need Gain approval for further investment in the Press Release (business justification) | Develop the full Press Release for funding approval Determine feasibility of each alternative solution | Finalize Product Roadmap and Release Planning Initiate Product Backlog Onboard the PM/Scrum Master and develop a Project Management Approach Kickoff the project | Define the details of the features and/or solution supporting achievement of the MVP Size stories in prioritized backlog (e.g. t-shirt sizes) and conduct sprint planning Establish acceptance criteria to support ‘done’ state from end user perspective | Execute work approved for sprint Conduct demonstration of completed features with product owner against acceptance criteria Agree on features to be release and quality assurance procedures | Conduct sprint retrospective for continuous improvement of team performance and execution Refine backlog and reprioritize based on Product Owner input/feedback | Finalize project management deliverables, transition to Operations Support team and closeout the project Actualize the business objectives and value from the Press Release Put the asset in service
Checklist | Begin Press Release: Executive Summary Scope and Boundaries Strategic Initiative Alignment Identify Business Sponsor Identify Product Owner Identify SMEs Identify and Involve Project Manager (Optional) Identify Technical Lead/Analyst (Optional) Estimate of Capital Investment Estimate of O&M Investment Proposed Project Request (PPR) / Expected Benefits Action Plan BU Driven Only: Skip stage/gate | Identify Primary Products or Deliverables Define High Level Milestones Plan Finalized Press Release (Service Now): Implementation Cost (Capital and O&M) Ongoing Annual O&M Cost Reduced Cost Benefits Avoided Cost Benefits Qualitative Risk Assessment Identify and Involve Project Manager (Optional) Identify Technical Lead/Analyst (Optional) BU Driven Only: Complete all except: Costs & Benefits Skip gate URB approved PEEM Phase 0 process | Complete IT Project Categorization Assign PM / Scrum master Identify Technical Lead/Analyst Identify owner for change plan Document GOES Model (template) Identify Impacted Business Processes Develop Initial Schedule (template) Ensure Project Codes Ready Complete QRA Complete Project Management Plan Approach Hold Project Kickoff Schedule Initial Steering Committee Meeting Define Minimum Viable Product Create and Obtain Approval of Product Roadmap Buildout Backlog of Epics Create Test Management Approach/Acceptance Criteria Identify needed RFIs or RFPs | Complete/Revise Quantitative Risks Assessment Complete/Revise Change Mgmt. Needs Assessment Create/Revise Change Mgmt. Plan (template) Establish/Revise User Stories Groom Backlog Agree on Sprint Scope Share Upcoming Release Features Revise Schedule and Financials | Validation of Acceptance Criteria Update Risks and Issues Define Test Cases Product feature demonstration Burndown and Velocity Metrics Monitor Story Point Debt Definitive Estimate gate is required after 20% of Sprints are completed | Update Project Risks/ Issues Document Lessons Learned Obtain IT Change Control Board Approval for Release Produce Test Case Results and Test Results Artifacts Document Release Deployment Plan Obtain Product Owner Acceptance of User Stories Conduct Release Readiness Review, obtain Acceptance from Operations and obtain Production Acceptance approval Distribute Release Notes, including UI and Feature – Function Descriptions | Complete Post Deployment Support (Hypercare) Close Project Risks and Issues Update Lessons Learned Put Work Order(s) In-Service Finalize Schedule Finalize Financials Finalize Project Artifact Archival Closeout project
 | Estimate Maturity: -50%/+100% | Estimate Maturity: -50%/+50% | Estimate Maturity: -50%/+50% | Estimate Maturity: -20%/+30% | Estimate Maturity: -10%/+15% | Estimate Maturity: -10%/+10% | Estimate Maturity: Actualized
Plan
Refine
CoE | Identify data flow in business process Identify platforms / applications impacted | Identify data entities for integration Estimate integration & data migration Support scoping & budgeting | Define Integration Roadmap Define Integration Architecture Review standards & define non- functional requirements Architecture Review Board review | Reuse analysis Define Acceptance criteria Identify system of record Identify frequency/ batch | Design review Finalize Deployment architecture vCore analysis | Code review Go-live checklist review Operation plan review Technical Debt review | Update exchange Update platform KPIs Review performance actual vs planned

## Slide 9: SDLC Categories
Waterfall | Iterative | Agile
Linear lifecycle that proceeds sequentially through the analysis phases. Each phase must be completed fully before the next phase can begin. This methodology aims at controlling project risk by requiring complete knowledge and precision in each phase of the process. It also provides more direct alignment between project funding and development gates. | Iterative is in-between a waterfall (purely sequential) and an agile approach. Typically, an iterative methodology performs Develop Concept, Develop Press Release, Project Initiation, Develop Initial Design (Analysis and High Level Design) once with a team and then carries out Design, Direct & Manage (Build, Test, and Deploy) multiple times to deliver functionality in large increments, possibly with another team. Then, Post Deployment is complete. This implies that a complete scope is identified and defined in advance of the iterative cycles. | Agile methodologies presume and mitigate the fact that requirements will evolve and change over the course of development. Agile practices solicit feedback through continuous testing and frequent product demonstrations. This feedback ensures that developers accurately understand the company's business objectives and that the software supports those objectives. Agile development methods rely on time-boxed sprints to limit scope and increase the speed of product delivery. One tenet of agile is that organizations should kill projects that, for one reason or another, no longer appear aligned with business strategy.
A definition of each SDLC methodology is provided below to align project leadership and decisions makers on the concept of each approach. Common characteristics to help determine which is most appropriate is included on the subsequent slide

## Slide 10: Project Methodology Attributes
The table below represents project attributes that assist in determining the appropriate execution methodology. This in formation should be used as reference to support method selection during the ‘Develop Press Release’ stage.
Scenario/attributes | Waterfall | Iterative | Agile
Changing Requirements |  |  | X
Unproven technology |  |  | X
Skilled developers: co-located, 100% allocated, adaptable & able to think independently |  |  | X
Rapid prototyping of the product is more important than the initial quality of the product |  |  | X
Many integrations and dependencies external to product and team | X |  | 
Definition, not speed, is key to success | X |  | 
Multi-component program where infrastructure and architecture are well defined while application interfaces are not defined in detail |  | X | 
Heavy regulatory and legal compliance elements | X | X | 
Significant infrastructure build and architectural work required | X | X | 
Complex requirements and design needed to create a foundation | X | X | 
Release management process not mature | X |  | 
Full time resource allocation not possible | X |  | 
Customer organization is not mature in product ownership and culturally accepting of agile methods |  |  | 

## Slide 11: SGP Tailoring for SDLC
Develop Press Release
Develop Initial Design
Design
Direct & Manage
Create Concept
Project Initiation
Post Deployment
Direct & Manage
Design
Test
Deploy
Build
Develop Press Release
Develop Initial Design
Create Concept
Project Initiation
Post Deployment
Plan
Sprint/
Release
Refine
Develop Press Release
Create Concept
Project Initiation
Post
Deployment
Waterfall
Iterative
Agile

## Slide 12: Waterfall / Iterative – SGP Tailoring for Categories
 | Required |  | Optional
Deliverable | Project Categorization |  |  |  | 
 | Formal Gated ( >$500k )* | Informal Gated (Greater than $250k - $500k) | Informal Gated (Less than $250k) | Miscellaneous Effort | Annual/Routine Effort
Press Release |  |  |  |  | 
Project Execution Plan (PEP) – including Project Charter and Project Management Plan |  |  |  |  | 
GOES Model (Steering Committee required for Formal and Informal Gated greater than $250K) |  |  |  |  | 
Qualitative Risk Assessment |  |  |  |  | 
Project Status Reports |  |  |  |  | 
Quantitative Risk Assessment |  |  |  |  | 
Schedule |  |  |  |  | 
Financials |  |  |  |  | 
Test Management Plan |  |  |  |  | 
Change Management Plan |  |  |  |  | 
Detailed Requirements Document |  |  |  |  | 
System Design Specs |  |  |  |  | 
Requirements Traceability Matrix |  |  |  |  | 
Project Change Request |  |  |  |  | 
Test Cases/Results Report |  |  |  |  | 
Runbook |  |  |  |  | 
Operational Readiness Signoff |  |  |  |  | 
Lessons Learned |  |  |  |  | 
Work Order In Service |  |  |  |  | 
Gate Scorecards/Approvals |  |  |  |  | 
Project Artifact Repository (Shared PMO Repository) |  |  |  |  | 
* The budget threshold for SGP categories may vary by tower. e.g. Towers may supply justifications for $5M and up to be formal gated with below that to be informal gated.

## Slide 13: Agile – SGP Tailoring for Categories
 | Required |  | Optional
Deliverable | Project Categorization |  |  |  | 
 | Formal Gated ( >$500k) * | Informal Gated (Greater than $250k - $500k) | Informal Gated (Less than $250k) | Miscellaneous Effort | Annual/Routine Effort
Press Release |  |  |  | Agile should not apply to these projects as they are too small and routine for Agile | 
GOES Model (Steering Committee required for Formal and Informal Gated greater than $250K) |  |  |  |  | 
Qualitative Risk Assessment |  |  |  |  | 
Project Management Approach |  |  |  |  | 
Project Status Reports |  |  |  |  | 
Quantitative Risk Assessment |  |  |  |  | 
Schedule |  |  |  |  | 
Financials |  |  |  |  | 
Test Management Approach/Acceptance Criteria |  |  |  |  | 
Change Management Plan |  |  |  |  | 
Minimum Viable Product |  |  |  |  | 
Product Roadmap |  |  |  |  | 
Backlog |  |  |  |  | 
Project Change Request |  |  |  |  | 
Test Cases/Results Report |  |  |  |  | 
Release Deployment Plan |  |  |  |  | 
Product Owner Acceptance |  |  |  |  | 
Release Notes |  |  |  |  | 
Work Order In Service |  |  |  |  | 
Gate Scorecards/Approvals |  |  |  |  | 
Project Artifact Repository (Shared PMO Repository) |  |  |  |  | 
* The budget threshold for SGP categories may vary by tower. e.g. Towers may supply justifications for $5M and up to be formal gated with below that to be informal gated.

## Slide 14: SGP Scorecards
Waterfall Template
Agile Template